## Instructions
Communtiy Efficiency Financing - Program Workbook
INSTRUCTIONS - PLEASE READ FIRST
As described in the application form the green highlighted tabs must be completed and submitted in parallel with the application submission. For Program Design & Evaluation Studies, the red highlighted tabs will need to be completed and submitted at the completion of your study. Please ensure that the requested information is completed within each of the relevant project workbook tabs. Note that a Payment and Reporting Table tab, and the Expense Claim tab will be provided only after your application is approved for funding. They are used to track your initiative's progress.
▪ MILESTONE: A milestone is a major deliverable or deliverables indicating the completion of one or more task. Disbursements will be made upon completion of determined milestones.
▪ START/END DATES: Enter the estimated start and end dates for each milestone. Projects must be completed within four years from the date a contract is executed between the recipient and FCM. This requirement will be noted in your contract with FCM.
▪ TASK: A task is defined as a single activity undertaken to achieve a milestone. For each task identified, provide a description of what the task entails, who will be completing the task, and estimate the cost. Individual tasks should generally be less than $50,000. Costs should be separated into eligible and ineligible categories. Refer to the eligible and ineligible costs tab for a list of costs that can be partially reimbursed by FCM.
▪ CONTINGENCY COSTS: Contingency costs are eligible, but cannot be listed as a separate budget item. Allocate contingency costs within the relevant budget items as and where appropriate, and add an explanation of the contingency percentage or amount in the “Contingency costs” section below the workplan table.
▪ TAXES: You may include the portion of taxes for which your organization is not eligible for a rebate (provincial, territorial, or federal) in your budget. Allocate this amount within the relevant tasks as and where appropriate.
▪ DELETING ROWS: Rows cannot be deleted, due to the template’s structure. Leave extra or empty rows blank.
▪ DATA CELLS & FORMULAS: Throughout the budget sheets, only input data into blue and yellow shaded cells. Do not delete or override cells which may contain formulas for calculations.

## Eligible and Ineligible Costs
Community Efficiency Financing - Eligible and Ineligible Costs |  |  | K1:P1K1:V1A1K1:L1K1:U1K1:V1A1K1:LK1:X1
This table outlines what costs can be partially reimbursed by FCM. Please pay particular attention to any costs that may be deemed ineligible by FCM.
Note: If your application is approved, expenses that are eligible for partial reimbursement must be:
· incurred after the date the application is received by FCM (with an exception being the cost to prepare the application incurred up to 90 days prior to the application receipt date).
· invoiced directly to your organization.
· an integral and an essential component of the initiative and required to help achieve the environmental objective of the initiative (e.g. installation of energy efficient equipment, renovation contractor outreach and training).
· actually and reasonably incurred in accordance with applicable industry standards.
· listed in a statement of expenses attached to an external audit report. You must keep all invoices, receipts and backup documents for seven years after the final FCM disbursement.
Cost Category | Eligible costs | Ineligible costs
Section A: Costs incurred prior to date application received by FCM
1) Pre-application | Consulting costs to write the GMF application incurred up to 90 days prior to application receipt date | All other costs incurred prior to application receipt date
Section B: Costs incurred after date application received by FCM
2) Administrative | Administrative costs that are directly linked to and have been incurred for the project such as: | Office space, supplies and general overhead costs incurred in the ordinary course of business.
• communication costs (e.g. long-distance calls or faxes)
• permits or certifications required for the project
• printing or photocopying by outside suppliers
• acquisition of documents used exclusively for the project
• document translation
3) Advertising | Advertising costs essential to communicating the project to relevant stakeholders, as well as project evaluation, such as: | • Advertising costs for general education or publicity that is a result of ongoing or other business activity and not a specific requirement of the project, such as:
| • advertising development | promotional items
• media distribution
• website development
• public surveys
4) Equipment rental | Rental of tools and equipment related to the project. | Rental of tools or equipment related to ongoing or other business activities.
5) Meetings and public gatherings | Costs related to meetings and public gatherings that communicate the project to the public and that collect feedback, such as: | Any hospitality expenses such as:
| · facility rental | · food and drink
| · audiovisual equipment rental | · alcohol
· door prizes
· entertainment
· music
· decorations, flowers, centerpieces, etc.
6) Services | Fees for professional or technical consultants and contractors. | Costs for engineering studies, audit studies or feasibility studies for which grants or contributions are provided by or committed to be provided by any program of the Government of Canada.
7) Staff Remuneration | Daily rates actually paid by the eligible recipient to its employees (including permanent and contract employees) in Canada for time actually worked on the implementation of the project. The daily rate per employee shall include the following costs: | • Overtime pay
| · Direct salaries: actual and justifiable sums paid by the eligible recipient to Employees in accordance with the eligible recipient’s pay scales as regular salary, excluding overtime pay and bonuses. | • Bonuses/performance pay
| · Fringe benefit, in accordance with the eligible recipient’s policies, as follows: | • Fringe benefits, such as sick days, maternity leave, parental leave, pension plan and any other fringe benefits not listed as eligible
| a) Time-off benefits (prorated to the annual percentage of time actually worked on the implementation of the project): allowable number of days to be paid by the eligible recipient for the payable absences of statutory holidays and annual vacation | • Costs related to ongoing or other regular business activities and not specifically required for the project
| b) Paid benefits: actual sums paid by the eligible recipient for paid benefits (prorated to the annual percentage of time actually worked on the implementation of the project): this includes the eligible recipient’s contribution to employment insurance and workers’ compensation plans (where applicable), health and medical insurance, group life insurance, and other mandatory government benefits. | • Staff wages while receiving training or attending learning events
• Professional membership fees or dues
| Note: For private (for-profit) entities only, as determined by FCM, the value of total staff remuneration cannot exceed 10% of the project's eligible costs. | • Staff remuneration for which FCM has provided (or committed to provide) a grant or contribution (this includes funding provided or committed through Climate Change Staff Grants from FCM’s Municipalities for Climate Innovation Program)
8) Supplies and materials (plans, studies and pilots) | Supplies and materials that are specifically needed to undertake the project. | Costs related to ongoing or other business activities that are not a specific requirement of the project.
9) Transportation, shipping and courier charges | Transportation costs for delivery of materials and services essential for the project. | Any transportation expense related to ongoing or other business activities.
10) Travel and accommodation | Travel and project-associated expenses for you and consultants, to the extent that the travel and accommodation rates comply with Treasury Board of Canada guidelines and to the extent the such travel is necessary to complete the project - including travel and accomodation costs to attend CEF capacity building activities organized by FCM. | • Travel, accommodation and fees to attend conferences, missions, trade shows, etc.
• Travel and associated expenses of a partner in the project.
11) Taxes | The portion of taxes for which your organization is not otherwise eligible for rebate. | The portion of taxes for which your organization is eligible for rebate (provincial, territorial, or federal).
13) In-kind | N/A
12) In-kind | N/A | Any goods and services that are received through donation or in-kind.
13) Training | Staff training necessary for the successful design and implementation of the program.
Costs associated with market building activities such as renovation contractor training, workforce skills development and energy advisor training.

## Environmental Benefits
Community Efficiency Financing - Environmental Benefits Quantification
Introduction
Overview
FCM's expectation is that your study will provide the environmental benefit information below. However, at this stage, please complete the tables below to the best of your ability and estimate the environmental benefits of the studied program. This tool has been developed to assist applicants in developing a high-level estimate of their program's GHG impacts, and to aid FCM in projecting the overall CEF impacts. This tool will not be used for program impact evaluation, and does not replace a feasibility study.
Important: Most calculations and background inputs in the workbook are fixed. Please fill in the Yellow and Blue cells as per the instructions below.
Please fill in the following yellow cells: 1) In Step 1, enter the Province/Territory where your program is/will be based. 2) In Step 2, enter information about the anticipated measures completed through your program. 3) In Step 3, review your program's projected benefits.
|  | Legend: | Yellow - cells that must be filled | Blue - cells that can be filled/modified
Step 1: Enter your Province / Territory
|  | What Province/Territory is your program based in? |  |  | Province/Territory: | ON
|  |  | GJ of energy used per household | tCO2e produced per household | tCO2e / GJ
|  | Electricity | 35.3893 | 0.19661 | 0.0055556
|  | Natural Gas | 68.7869 | 3.3474 | 0.048664
|  | Heating Oil | 2.871 | 0.20359 | 0.070911
|  | Wood | 9.6158 | 0.2258 | 0.023482
|  | Other | 2.473 | 0.15124 | 0.061156
|  | TOTAL | 119.136 | 4.1247 | 0.034622
Step 2: Estimate High-Level Program Uptake
Please fill in this section indicating: 1) The total number of participating homes you anticipate over the program duration 2) The expected breakdown between deep energy and light energy retrofits (descriptions provided below for guidance) 3) The expected number of renewable energy projects (these can be stand alone or in conjunction with the home energy retrofits) 4) Whether your program will support space heating electrification measures, such as converting a home from an oil or gas furnace to an electric heat pump The % energy savings for each measure are provided as a high-level guideline. Please add a note in column (I) if you would like to qualify any details about your program's deep or light energy retrofits that may be relevant. Further details can also be provided in your application narrative document. Note that the list of potential measures can be provided in the full application form, in question B7 Program Benefits, but does not have to be provided in this workbook. If desired, you may enter an additional measure in the "Other" row, completing the estimate energy consumption reduction for the average home, and providing a description of the measure in column (I). The main application form also includes space for additional details to be provided.
Deep energy retrofits refers to multi-measure, whole-home retrofits that include: significant envelope/insulation improvements, as well as upgrades to major pieces of equipment such as furnaces, water heaters, and air conditioners. Light energy retrofits are less comprehensive projects, that may include simple air-sealing measures, or replacement of just the heating and/or cooling equipment.
|  | Total number of participating homes: |  | 160
|  | Measure Category | Number of upgrade projects | Average energy consumption reduction | Note
|  | Unit | # | %
Energy Efficiency
|  | Deep energy retrofits | 160 | 33.39% | This project will aim for the Passive House EnerPHit standard of 70% reduction OR the equivalent of 30kWh per metre squared.
|  | Light energy retrofits | 0 | 15.68%
Renewable Energy
|  | Solar PV (5 kW system) | 20 | 19.22% | One 5 kW installation per eight unit townhome structure on average is anticipated. Optional Solar PV system may provide electricity for on-demand hot water systems for the buildings.
|  | Solar Thermal | 0 | 7.619%
Additional
|  | Other | 160 | 75% | Individual heat pumps and HRV's sourced from Lakefront Utility Services Inc. or Hydro One .
|  | Is heating electrification eligible in your program? |  |  | Yes
Step 3: Review Projected Program Benefits
Once you have completed Steps 1 and 2, please take a moment to review the projected program benefits in the table below. You may indicate in your application any important differences between what you may have determined your program benefits to be and what is quantified in this worksheet.
|  |  | Total anticipated energy consumption reduction | Total anticipated GHG emission reduction | Baseline energy consumption | Baseline GHG emission | % energy consumption reduction | % GHG emission reduction
|  |  | GJ/yr | tCO2e/yr | GJ/yr | tCO2e/yr | % | %
|  | Program Total | 21118.5919 | 706.1494 | 19061.7673 | 659.9486 | 110.8% | 107%

## Budget - Work Plan
WORK PLAN AND BUDGET
Lead applicant: | Town of Cobourg |  |  | Applicant type (select one) |  | Municipal
Project title: | Town of Cobourg – Feasibility Study – Community Efficiency Financing |  |  | Project type (select one) |  | Feasibility Study
Milestones | Start date: | End date: | Cost category (select one) | Eligible cost ($) | Ineligible cost ($) | Total cost ($)
Milestone 1: Draft Application to FCM. | 2020-10-15 | 2020-10-29
Milestone description: Costs to write the GMF application incurred up to 90 days prior to application receipt date.
Grant Writer pay/benefits for time required to draft full application. | 2020-10-15 | 2020-10-29 | (1) Pre-application | 3500 | 0 | 3500
Subtotal | [5 empty] | 3500 | 0
Milestone 2: Set Up Project Administration. | 2021-05-19 | 2022-06-30
Milestone description: Implement Team workplan, timeline, and support system needed to develop a professionally prepared draft Feasibility Study.
Pending application success, complete initial Team meeting to review/sign the FCM Contribution Agreement and confirm internal meeting schedule (as presented below). | 2021-05-19 | 2021-06-04 |  |  |  | 0
Hire part-time staff to support the Town of Cobourg in preparing an RFP. Purpose of the RFP will be to contract a Consultant for the proposed Feasibility Study for net-zero deep energy neighbourhood retrofits for low income residents. | 2021-05-19 | 2021-06-30 | (6) Services | 11000 |  | 11000
Time of a part-time staff to work on this project and support the Team for a one-year period (apprpox) providing technical and administrative support. | 2021-07-01 | 2023-03-31 | (6) Services | 22000 |  | 22000
Hold second Team meeting to develop purpose, goals, and criteria content for RFP for proposed Feasibility Study. | 2021-09-01 | 2021-09-15 |  |  |  | 0
Part-time staff (as noted in cell A12) to prepare the RFP to hire a Consultant (who will complete the Feasibility Study) and to develop a points system to grade responses in bids received. | 2021-09-15 | 2021-09-30 |  |  |  | 0
Hold third team meeting to review draft RFP for proposed Feasibility Study and points system. | 2021-10-01 | 2021-10-08 |  |  |  | 0
Town of Cobourg's Solicitor/Lawyer and Council to review RFP. | 2021-10-08 | 2021-10-15 |  |  |  | 0
Send out RFP "To Research, Analyze, and Detail the Pros and Cons of a Variety of Financing Models to Support Neighbourhood Deep Energy Retrofits for Low-income Residents." | 2021-10-18 | 2021-10-22 |  |  |  | 0
Part-time staff member (as noted in cell A12) to organize/summarize RFP responses AND forward to Team members for review. | 2021-10-25 | 2021-11-05 |  |  |  | 0
Hold fourth Team meeting to review/select a Consultant who will be tasked with preparing the proposed Feasibility Study. | 2021-11-08 | 2021-11-10 |  |  |  | 0
Consultant contacted and date for first meeting with Team arranged. | 2021-11-10 | 2021-11-10 |  |  |  | 0
Approval of winning bid and Start-up meeting with selected Consultant | 2021-11-10 | 2021-11-24 | (6) Services | 52000 |  | 52000
Consultant prepares for review first draft of Feasibility Study from Consultant on financing options that fit with the intended audience of landlords, low-income renters, and low income property owners facing 'energy poverty'. | 2021-11-29 | 2022-03-31 |  |  |  | 0
Administrator circulates draft to team for 1 week review and collects comments for review at the next meeting | 2022-04-01 | 2202-04-15
Hold fifth Team meeting to consolodate comments and convey them to the Consultant | 2022-04-18 | 2022-04-22
Consultant takes Team comments and preparesa for review a second draft of Feasibility Study on financing deep retrofits in neighbourhoods facing energy poverty before ta wider public consultation process starts. | 2022-04-25 | 2022-05-16 |  |  |  | 0
Subtotal | [5 empty] | 85000 | 0
Milestone 3: Public and Peer Consultation. | 2022-05-16 | 2022-09-09
Milestone description: Public input and sharing with peer organizations and stakeholders on the financing strategies coaleses around one or two options.
Meeting date to be announced regarding upcoming public consultation and draft Feasibility Study posted on the Town of Cobourg's website. | 2022-05-16 | 2022-05-20 |  |  |  | 0
One public consultation live or by Zoom with a rapporteur and the Consultant present and several means of expressing preferences. | 2022-06-15 | 2022-06-30 | (5) Meetings and public gatherings | 750 |  | 750
Part-time staff member (as noted in cell A12) will prepare a consultation report (that summarizes the consultation meeting outcomes/comments). and distributes for one week review to the Team | 2022-06-30 | 2022-07-15 |  |  |  | 0
Sixth Team meeting to review consultation report (as noted in cell A30). | 2022-07-18 | 2022-07-22 |  |  |  | 0
Revision of the Feasibility Report by Consultant under Team administrators direction. | 2022-07-25 | 2022-07-29 |  |  |  | 0
Share Report with peers (such as Recover N.S., PCP Climate Coordinator colleagues in eastern Ontario and Clean Air Partnership) for comment and with local stakeholder organizations. | 2022-08-01 | 2022-08-12 |  |  |  | 0
Part-time staff (as noted in cell A12) prepares report on comments from peer organizations and local stakeholders. | 2022-08-15 | 2022-08-19 |  |  |  | 0
Seventh Team meeting with Consultant to go over peer reports. | 2022-08-22 | 2022-08-26 |  |  |  | 0
Consultant to complete final revision of Feasibility Study taking into account direction from the Team on peer reports. | 2022-08-29 | 2022-09-02 |  |  |  | 0
Team meeting for final review before Feasibility Study goes to Committee of the Whole Cobourg Council. | 2022-09-05 | 2022-09-08 |  |  |  | 0
Subtotal | [5 empty] | 750 | 0
Milestone 4: Council Approval. | 2022-09-09 | 2022-09-26
Milestone description: Steps to achieve Council approval.
Deadline for Council meeting Agenda items. | 2022-09-05 | 2022-09-09 |  |  |  | 0
Council Committee of the Whole to review draft Feasibility Study. | 2022-09-12 | 2022-09-12 |  |  |  | 0
Motion to approve Feasibility Study by Cobourg Council. | 2022-09-26 | 2022-09-26 |  |  |  | 0
Total Project HST (13%) that won't be rebated to the Municipality @ 1.76% | 2020-01-01 | 2022-12-31 | (11) Taxes | 205 |  | 205
Subtotal | [5 empty] | 205 | #REF!
Milestone 5: Report on Process to FCM funder | 2022-10-03 | 2023-03-31
Prepare a report on FCM / GMF 17564 Town of Cobourg F5-CEF Agreement for funder.
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
Subtotal | [5 empty] | 0 | 0
Total – All phases |  |  |  | 89400 | 0 | 89400
|  |  | Note: The costs under "Total - All phases" are rounded down to the nearest $100. | Total eligible costs |  | 89400
Contingency costs: Have you included room for contingencies in some or all of your task costs? Please explain.
Contingency costs are included in the budget to allow for uncertainties resulting from the COVID-19 pandemic such as: the number of RFP responses received for the Consultant contract, the amount of time it may take for the Consultant to fulfill their duties, as well as the practicality of face-to-face public consultations which may or may not be fulfilled via virtual public consultations.
Other notes:
Advanced contribution (prior to GMF verification)
Total advanced contribution allowable | 0
To be eligible for an advanced contribution applicants must have all sources of funding confirmed and their project delivery team in place. FCM will conduct a risk assessment upon approval of your application to determine the total allowable advanced contribution. Based on applicant type, the following maximum amounts may be available: -Municipalities and municipally owned corporations may be eligible to receive up to 70% grant funding upfront at the time of grant agreement signature. -NGOs and other non-profit entities may be eligible to receive up to 50% of grant funding upfront at the time of grant agreement signature. -For-profit entities, as determined by FCM, are not eligible for an advanced contribution
Would you like to be considered for an advanced contribution? (select YES or NO)
YES
NO
Municipal
Municipally Owned Corporation
NGO/Other
Private
Feasibility Study
Program Design Study
Program Evaluation Study
(1) Pre-application
(2) Administrative
(3) Advertising
(4) Equipment rental
(5) Meetings and public gatherings
(6) Services
(7) Staff remuneration
(8) Supplies and materials
(9) Transportation, shipping and courier charges
(10) Travel and accommodation
(11) Taxes
(12) In-Kind
(13) Training

## Sources of Funding
Community Efficiency Financing - Sources of Funding
INSTRUCTIONS Enter all funding sources for your study. For each funding source, please indicate the amount of the funding, and when the funding is confirmed or expected to be confirmed. The total of all funding sources must equal the total study costs in your Budget table (tab Budget - Workplan). All sources of funding must be confirmed in writing and submitted to FCM prior to the first disbursement. Note: Funding is provided for up to 80% of eligible study costs. The spreadsheet will auto-calculate the maximum eligible GMF grant amounts according to the Total Eligible Costs in the budget. FCM will cap the GMF grant amounts according to the other confirmed sources of funding.
Fund Source | Description | Funding Type | Confirmed (Y/N) | Date Committed MM-DD-YYYY | Amount | Percentage of Total Budget
Green Municipal Fund | Grant | GMF | NO |  | 71520 | 80%
Lead Applicant - Town of Cobourg | Cash | Municipal | YES | Dec 15, 2019 | 17880 | 20%
Additional Funding Source (please be specific) | [5 empty] | 0%
Additional Funding Source (please be specific) | [5 empty] | 0%
Additional Funding Source (please be specific) | [5 empty] | 0%
Additional Funding Source (please be specific) | [5 empty] | 0%
Additional Funding Source (please be specific) | [5 empty] | 0%
Additional Funding Source (please be specific) | [5 empty] | 0%
Total Funding: |  |  |  |  | 89400 | 100%
[Total should be equal to the sum indicated in the budget - Work Plan tab]
|  |  |  | Budget Total Costs |  | 89400
|  |  |  | Budget Total Eligible Costs |  | 89400
Note: Total Funding MUST EQUAL Budget Total Costs
Description List | Funding Type list
Loan | Federal | YES
Grant | Provincial | NO
Cash | Municipal
In-kind | Private
GMF

## MilestoneSummary
Community Efficiency Financing - Milestone Summary
Milestone | Milestone Description | Start Date (mm/dd/yy)* | End Date (mm/dd/yy)* | Estimated Total Operating Cost ($)
A short summary of key activities to be undertaken by applicant
Milestone 1: Draft Application to FCM. | Milestone description: Costs to write the GMF application incurred up to 90 days prior to application receipt date. | 2020-10-15 | 2020-10-29 | 3500
Milestone 2: Set Up Project Administration. | Milestone description: Implement Team workplan, timeline, and support system needed to develop a professionally prepared draft Feasibility Study. | 2021-05-19 | 2022-06-30 | 85000
Milestone 3: Public and Peer Consultation. | Milestone description: Public input and sharing with peer organizations and stakeholders on the financing strategies coaleses around one or two options. | 2022-05-16 | 2022-09-09 | 750
Milestone 4: Council Approval. | Milestone description: Steps to achieve Council approval. | 2022-09-09 | 2022-09-26 | 205
0
0
TOTAL |  |  |  | 89455

## Environmental Benefits - Post
Community Efficiency Financing - Environmental Benefits Quantification
Introduction
Overview
Please use the information provided in your study to complete the tables below. This tool has been developed to assist applicants in developing a high-level estimate of their program's GHG impacts, and to aid FCM in projecting the overall CEF impacts. This tool will not be used for program impact evaluation, and does not replace a feasibility study.
Important: Most calculations and background inputs in the workbook are fixed. Please fill in the Yellow and Blue cells as per the instructions below.
Please fill in the following yellow cells: 1) In Step 1, enter the Province/Territory where your program is based. 2) In Step 2, enter information about the anticipated measures completed through your program. 3) In Step 3, review your program's projected benefits.
|  | Legend: | Yellow - cells that must be filled | Blue - cells that can be filled/modified
Step 1: Enter your Province / Territory
|  | What Province/Territory is your program based in? |  |  | Province/Territory: | MB
|  |  | GJ of energy used per household | tCO2e produced per household | tCO2e / GJ
|  | Electricity | 62.0844 | 0.036216 | 0.00058333
|  | Natural Gas | 42.8578 | 2.0834 | 0.048613
|  | Heating Oil | 0.22503 | 0.015957 | 0.070911
|  | Wood | 6.6242 | 0.15555 | 0.023482
|  | Other | 0.32007 | 0.019576 | 0.061163
|  | TOTAL | 112.1114 | 2.3107 | 0.020611
Step 2: Estimate High-Level Program Uptake
Please fill in this section indicating: 1) The total number of participating homes you anticipate over the program duration 2) The expected breakdown between deep energy and light energy retrofits (descriptions provided below for guidance) 3) The expected number of renewable energy projects (these can be stand alone or in conjunction with the home energy retrofits) 4) Whether your program will support space heating electrification measures, such as converting a home from an oil or gas furnace to an electric heat pump The % energy savings for each measure are provided as a high-level guideline. Please add a note in column (I) if you would like to qualify any details about your program's deep or light energy retrofits that may be relevant. Further details can also be provided in your application narrative document. Note that the full list of program eligible measures is requested in the main application form, in question B7 Environmental benefits, but does not have to be provided in this workbook. If desired, you may enter an additional measure in the "Other" row, completing the estimate energy consumption reduction for the average home, and providing a description of the measure in column (I). The main application form also includes space for additional details to be provided.
Deep energy retrofits refers to multi-measure, whole-home retrofits that include: significant envelope/insulation improvements, as well as upgrades to major pieces of equipment such as furnaces, water heaters, and air conditioners. Light energy retrofits are less comprehensive projects, that may include simple air-sealing measures, or replacement of just the heating and/or cooling equipment.
|  | Total number of participating homes: |  | 20
|  | Measure Category | Number of upgrade projects | Average energy consumption reduction | Note
|  | Unit | # | %
Energy Efficiency
|  | Deep energy retrofits | 15 | 33.39%
|  | Light energy retrofits | 5 | 15.68%
Renewable Energy
|  | Solar PV (5 kW system) | 0 | 20.42%
|  | Solar Thermal | 0 | 7.619%
Additional
|  | Other |  | 0%
|  | Is heating electrification eligible in your program? |  |  | No
Step 3: Review Projected Program Benefits
Once you have completed Steps 1 and 2, please take a moment to review the projected program benefits in the table below. You may indicate in your application any important differences between what you may have determined your program benefits to be and what is quantified in this worksheet.
|  |  | Total anticipated energy consumption reduction | Total anticipated GHG emission reduction | Baseline energy consumption | Baseline GHG emission | % energy consumption reduction | % GHG emission reduction
|  |  | GJ/yr | tCO2e/yr | GJ/yr | tCO2e/yr | % | %
|  | Program Total | 649.3475 | 12.4354 | 2242.228 | 46.2147 | 28.96% | 26.91%

## OperatingBudget
Community Efficiency Financing - Work Plan and Operating Budget
Lead applicant: |  |  |  | Applicant type (select one)
Project title: |  |  |  | Project type (select one)
Milestones | Start date: | End date: | Cost category (select one) | Eligible cost ($) | Ineligible cost ($) | Total cost ($)
Program Start-up | mm/yyyy | mm/yyyy
Milestone description: [e.g Research, legal and progam design activities in preparation for program launch]
Pace Legal Opinion |  |  | (6) Services |  |  | 0
Website Development |  |  | (2) Administrative |  |  | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
Subtotal | [5 empty] | 0
Year 1 Implementation | mm/yyyy | mm/yyyy
Milestone description: [e.g. Undertake home energy retrofits and deliver financing]
National peer learning workshops convened by FCM (travel & accommodation for up to 3 project team members) |  |  | (10) Travel and accommodation |  |  | 0
Staffing Program Coordinator Salary |  |  | (7) Staff remuneration |  |  | 0
Design of Promotional Collateral |  |  | (6) Services |  |  | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
Subtotal | [5 empty] | 0
Year 2 Implementation | mm/yyyy | mm/yyyy
Milestone description: [In this box, please describe the milestone or the major deliverable that indicates the completion of this milestone]
National peer learning workshops convened by FCM (travel & accommodation for up to 3 project team members) |  |  | (12) Travel and accommodation |  |  | 0
Staffing Program Coordinator Salary |  |  | (7) Staff remuneration |  |  | 0
Promotional brochures |  |  | (3) Advertising |  |  | 0
Billing Systems IT upgrades |  |  | (2) Administrative |  |  | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
Subtotal | [5 empty] | 0
Year 3 Implementation | mm/yyyy | mm/yyyy
Milestone description: [In this box, please describe the milestone or the major deliverable that indicates the completion of this milestone]
National peer learning workshops convened by FCM (travel & accommodation for up to 3 project team members) |  |  | (12) Travel and accommodation |  |  | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
Subtotal | [5 empty] | 0
Year 4 Implementation | mm/yyyy | mm/yyyy
Milestone description: [In this box, please describe the milestone or the major deliverable that indicates the completion of this milestone]
National peer learning workshops convened by FCM (travel & accommodation for up to 3 project team members) |  |  | (12) Travel and accommodation |  |  | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
Subtotal | [5 empty] | 0
Program Wrap-up | mm/yyyy | mm/yyyy
Milestone description: [e.g Perform progam evaluation and final reporting]
Report writing |  |  | (8) Services |  |  | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
[Add task description here] | [5 empty] | 0
Subtotal | [5 empty] | 0
Total – All phases |  |  |  | 0 | 0 | 0
|  |  | Note: The costs under "Total - All phases" are rounded down to the nearest $100. | Total eligible costs |  | 0
Contingency costs: Have you included room for contingencies in some or all of your task costs? Please explain.
[Add explanation about contingency here]
Other notes:
[Add any other relevant details about your work plan and budget here]
Municipal
Municipally Owned Corporation
NGO/Other
Private
Feasibility Study
Program Design Study
Program Evaluation Study
(1) Pre-application
(2) Administrative
(3) Advertising
(4) Equipment rental
(5) Meetings and public gatherings
(6) Services
(7) Staff remuneration
(8) Supplies and materials
(9) Transportation, shipping and courier charges
(10) Travel and accommodation
(11) Taxes
(12) In-Kind
(13) Training

## CapitalBudget
Community Efficiency Financing - Capital Budget
Milestone | Home Energy Upgrade Projects (#) |  |  | Average Cost of Project ($) | Average Incentive or Rebate provided by third-party ($) | Total Incentives or Rebates provided by Lead Applicant ($) | Total Capital Expenditure Forecast ($)
| Estimate of the total number of home energy upgrade projects to be completed |  |  | Estimate of aveage cost of home energy upgrades including energy assessments, equipment and material, labour and taxes, as applicable | Estimate of average incentive or rebate per home energy upgrade project | Actual rebates and incentives included in the Operating Budget | Total expenditure of home energy upgrades net of incentives/rebates
Year 1 Implementation | [5 empty] | 0 | 0
Year 2 Implementation | [5 empty] | 0 | 0
Year 3 Implementation | [5 empty] | 0 | 0
Year 4 Implementation | [5 empty] | 0 | 0
TOTAL | 0 |  |  | 0 | 0 |  | 0
Note: totals are rounded down to the nearest $100
Note to applicant:
Identify the source of capital to be used for lending to homeowners for home energy upgrade projects (indicate with an X) and percentage (%) for each funding source
%
GMF
Municipal
Third-party |  |  | Name of third-party lender:
TOTAL |  | 0%

## Payment & reporting table (hidden)
Payment and reporting table
Contribution(s) and Deliverable(s) | Expected Date of Contribution |  | The Contribution shall be equal to: | [EXAMPLE] Project Officer to insert customized table
Advanced Contribution #1 | Within 30 days of executed Agreement + receipt of void cheque |  | $INSERT AMOUNT CALCULATED AT TIME OF PROJECT APPROVAL
· Executed Grant Agreement
· Void Cheque
Contribution(s) and Deliverable(s) | Approximate Date of Submission | Approximate Date of Contribution | The Contribution shall be equal to the lesser of:
Contribution #2 | INSERT DATE GMF EXPECTS TO RECEIVE COMPLETED REQUEST | INSERT DATE 30 DAYS AFTER SUBMISSION DATE | $INSERT COMBINED AMOUNT OF CONTRIBUTIONS 1 AND 2, THIS MUST BE A MAXIMUM OF 75% OF TOTAL GRANT less the amount of previous Contributions; or INSERT 50 OR 80 AS IDENTIFIED IN APPROVAL% of Eligible Costs then incurred by the Recipient less the amount of previous Contributions
· Schedule D – Request for Contribution
· Schedule E – Project Progress Report
· Evidence that Milestones INSERT APPROPRIATE NUMBERS FROM THE WORKBOOK were completed: INSERT DELIVERABLES IDENTIFIED IN PROJECT WORKBOOK
· Updated Project Workbook
o Sources of Funding
o Payment and Reporting Schedule
o Expense Claim
· Additional conditions: INSERT ANY EXTRA CONDITIONS IMPOSED BY GMF STAFF OR GMF COUNCIL/FCM BOARD OR WRITE None
Final Contribution | INSERT DATE GMF EXPECTS TO RECEIVE COMPLETED REQUEST | INSERT DATE 30 DAYS AFTER SUBMISSION DATE | $INSERT TOTAL GRANT AMOUNT less the amount of previous Contributions; or INSERT 50 OR 80 AS IDENTIFIED IN APPROVAL% of Eligible Costs then incurred by the Recipient less the amount of previous Contributions
· Schedule D – Request for Contribution
· Schedule F – Project Completion Report
· Evidence that Milestones INSERT APPROPRIATE NUMBERS FROM THE WORKBOOK were completed : INSERT DELIVERABLES IDENTIFIED IN PROJECT WORKBOOK
· Updated Project Workbook
o Sources of Funding
o Payment and Reporting Schedule
o Expense Claim
· Final INSERT NAME OF FINAL DELIVERABLE (S)
· IF PLAN, INSERT ''Evidence of municipal council approval''
· Additional conditions: INSERT ANY EXTRA CONDITIONS IMPOSED BY GMF STAFF OR GMF COUNCIL/FCM BOARD OR WRITE None

## Expense Claim (hidden)
Expense claim - GMF Initiatives
Lead Applicant: | Town of Cobourg |  |  |  |  | Indicate tax rebate rate ------->
Project title: | Town of Cobourg – Feasibility Study – Community Efficiency Financing
Estimated budget costs (from tab 3. Budget - Workplan) | [6 empty] | Actual budget costs
Milestones | Start date: | End date: | Cost category | Eligible cost ($) | Ineligible cost ($) | Total predicted cost ($) | Actual eligible cost (net of tax-rebate) | Actual ineligible cost (net of tax rebate) | Total actual costs (net of tax rebate) | Recipient comments | GMF comments
Milestone 1: Draft Application to FCM. | 2020-10-15 | 2020-10-29
Milestone description: Costs to write the GMF application incurred up to 90 days prior to application receipt date.
Grant Writer pay/benefits for time required to draft full application. |  |  | (1) Pre-application | 3500 | 0 | 3500 |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
Subtotal |  |  |  | 0 | 0 | 3500 | 0 | 0 | 0
Milestone 2: Set Up Project Administration. | 2021-05-19 | 2022-06-30
Milestone description: Implement Team workplan, timeline, and support system needed to develop a professionally prepared draft Feasibility Study.
Hire part-time staff to support the Town of Cobourg in preparing an RFP. Purpose of the RFP will be to contract a Consultant for the proposed Feasibility Study for net-zero deep energy neighbourhood retrofits for low income residents. |  |  | (6) Services | 11000 | 0 | 11000 |  |  | 0
Time of a part-time staff to work on this project and support the Team for a one-year period (apprpox) providing technical and administrative support. |  |  | (6) Services | 22000 | 0 | 22000 |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
Part-time staff (as noted in cell A12) to prepare the RFP to hire a Consultant (who will complete the Feasibility Study) and to develop a points system to grade responses in bids received. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Hold second Team meeting to develop purpose, goals, and criteria content for RFP for proposed Feasibility Study. |  |  | 0 | 0 | 0 | 0 |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
Hold third team meeting to review draft RFP for proposed Feasibility Study and points system. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Town of Cobourg's Solicitor/Lawyer and Council to review RFP. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Send out RFP "To Research, Analyze, and Detail the Pros and Cons of a Variety of Financing Models to Support Neighbourhood Deep Energy Retrofits for Low-income Residents." |  |  | 0 | 0 | 0 | 0 |  |  | 0
Part-time staff member (as noted in cell A12) to organize/summarize RFP responses AND forward to Team members for review. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Hold fourth Team meeting to review/select a Consultant who will be tasked with preparing the proposed Feasibility Study. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Consultant contacted and date for first meeting with Team arranged. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Approval of winning bid and Start-up meeting with selected Consultant |  |  | (6) Services | 52000 | 0 | 52000 |  |  | 0
Consultant prepares for review first draft of Feasibility Study from Consultant on financing options that fit with the intended audience of landlords, low-income renters, and low income property owners facing 'energy poverty'. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Consultant takes Team comments and preparesa for review a second draft of Feasibility Study on financing deep retrofits in neighbourhoods facing energy poverty before ta wider public consultation process starts. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Subtotal |  |  |  | 0 | 0 | 85000 | 0 | 0 | 0
Milestone 3: Public and Peer Consultation. | 2022-05-16 | 2022-09-09
Milestone description: Public input and sharing with peer organizations and stakeholders on the financing strategies coaleses around one or two options.
One public consultation live or by Zoom with a rapporteur and the Consultant present and several means of expressing preferences. |  |  | (5) Meetings and public gatherings | 750 | 0 | 750 |  |  | 0
Part-time staff member (as noted in cell A12) will prepare a consultation report (that summarizes the consultation meeting outcomes/comments). and distributes for one week review to the Team |  |  | 0 | 0 | 0 | 0 |  |  | 0
Sixth Team meeting to review consultation report (as noted in cell A30). |  |  | 0 | 0 | 0 | 0 |  |  | 0
Revision of the Feasibility Report by Consultant under Team administrators direction. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Share Report with peers (such as Recover N.S., PCP Climate Coordinator colleagues in eastern Ontario and Clean Air Partnership) for comment and with local stakeholder organizations. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Part-time staff (as noted in cell A12) prepares report on comments from peer organizations and local stakeholders. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Seventh Team meeting with Consultant to go over peer reports. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Consultant to complete final revision of Feasibility Study taking into account direction from the Team on peer reports. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Team meeting for final review before Feasibility Study goes to Committee of the Whole Cobourg Council. |  |  | 0 | 0 | 0 | 0 |  |  | 0
Deadline for Council meeting Agenda items. |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
Council Committee of the Whole to review draft Feasibility Study. |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
Motion to approve Feasibility Study by Cobourg Council. |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
Subtotal |  |  |  | 0 | 0 | 750 | 0 | 0 | 0
Milestone 4: Council Approval. | 2022-09-09 | 2022-09-26
Milestone description: Steps to achieve Council approval.
#REF! |  |  | 0 | 0 | 0 | 0 |  |  | 0
#REF! |  |  | 0 | 0 | 0 | 0 |  |  | 0
#REF! |  |  | 0 | 0 | 0 | 0 |  |  | 0
Total Project HST (13%) that won't be rebated to the Municipality @ 1.76% |  |  | (11) Taxes | 205 | 0 | 205 |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
Subtotal |  |  |  | #REF! | #REF! | #REF! | 0 | 0 | 0
#REF! | #REF! | #REF!
#REF!
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
#REF! |  |  | #REF! | #REF! | #REF! | #REF! |  |  | 0
Subtotal |  |  |  | 0 | 0 | 205 | 0 | 0 | 0
Milestone 5: Report on Process to FCM funder | 2022-10-03 | 2023-03-31
Prepare a report on FCM / GMF 17564 Town of Cobourg F5-CEF Agreement for funder.
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
[Add task description here] |  |  | 0 | 0 | 0 | 0 |  |  | 0
Subtotal |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 89400 | 0 | 89400 | 0 | 0 | 0
FOR USE BY GMF - CONTRIBUTION SECTION |  |  |  |  | X Current and previous Disbursements | Amount | Total actual eligible costs |  | 0
Disbursement #1 as per GMF records | [6 empty] | Total available grant |  | 0
Disbursement #2 as per GMF records
Disbursement #3 as per GMF records
Total amount disbursed to date as per GMF records
Total amount available for disbursement (amount identified in the grant agreement less the total amount disbursed to date) | [5 empty] | 0
(1) Pre-application
(2) Administrative
(3) Advertising
(4) Capital Expenditures
(5) Equipment rental
(6) In-Kind
(7) Meetings and public gatherings
(8) Services
(9) Staff remuneration
(10) Supplies and materials
(11) Transportation, shiping and courier charges
(12) Travel and accommodation
(13) Taxes

## Calculations (hidden)
Environmental Benefits Quantification
Program Uptake and Results Calculations
|  | Measure Category | Number of upgrade projects | Deep Retrofit Measures | Light Retrofit Measures | Average energy consumption reduction in the category | Average energy consumption of category as percentage of home | Average energy consumption reduction | Average GHG Emission Reduction | Note
|  | Unit | # | Select | Select | % | % | GJ/yr | tCO2e/yr
Energy Efficiency
|  | Deep home retrofit | 160 | N/A | N/A | 40.56% | 82.31% | 39.7772 | 1.304
|  | Light home retrofit | 0 | N/A | N/A | 19.04% | 82.31% | 18.6753 | 0.57345
|  | Individual measures: | Direct input as alternative to providing numbers above
|  | Space Heating | 160 | x | x | 20% | 56.06% | 13.3574 | 0.46245
|  | Insulation | 160 | x |  | 30% | 56.06% | 20.036 | 0.69368
|  | Space Cooling | 160 | x | x | 15% | 2.982% | 0.5329 | 0.01845
|  | Insulation | 160 | x |  | 30% | 2.982% | 1.0658 | 0.036899
|  | Lighting | 160 | x | x | 50% | 4.223% | 2.5158 | 0.013977
|  | Water Heating | 160 | x | x | 10% | 19.05% | 2.2693 | 0.078565
|  | Fuel Switching (NG) | 0 |  |  | 43.4% | 56.06% | 28.9855 | 2.1764 | Space heating only; Natural Gas to Elec Heat Pump
|  | Fuel Switching (Oil) | 0 |  |  | 48.16% | 56.06% | 32.1645 | 3.2341 | Space heating only; Oil to Elec Heat Pump
Renewable Energy
|  | Solar PV (5 kW system) | 20 | N/A | N/A | 19.22% | 100%
|  | Solar Thermal | 0 | N/A | N/A | 40% | 19.05%
Program Benefits Breakdown
|  |  | Program Benefits |  | Baseline |  | Comparison
|  | Measure Category | Total anticipated energy consumption reduction | Total anticipated GHG emission reduction | Baseline energy consumption | Baseline average household GHG emission | % energy consumption reduction | % GHG emission reduction
|  | Unit | GJ/yr | tCO2e/yr | GJ/yr | tCO2e/yr | % | %
Energy Efficiency
|  | Deep home retrofit | 6364.3469 | 208.6439 | 19061.7673 | 659.9486 | 33.39% | 31.62%
|  | Light home retrofit | 0 | 0 | 0 | 0 | 0% | 0%
Renewable Energy
|  | Solar PV (5 kW system) | 457.9196 | 2.544 | 2382.7209 | 82.4936 | 19.22% | 3.084%
|  | Solar Thermal | 0 | 0 | 0 | 0 | 0% | 0%
Other
|  | Other | 14296.3255 | 494.9615 | 19061.7673 | 659.9486 | 75% | 75%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hide & password protect - for FCM internal only

## Calculations2 (hidden)
Environmental Benefits Quantification
Program Uptake and Results Calculations
|  | Measure Category | Number of upgrade projects | Deep Retrofit Measures | Light Retrofit Measures | Average energy consumption reduction in the category | Average energy consumption of category as percentage of home | Average energy consumption reduction | Average GHG Emission Reduction | Note
|  | Unit | # | Select | Select | % | % | GJ/yr | tCO2e/yr
Energy Efficiency
|  | Deep home retrofit | 15 | N/A | N/A | 40.56% | 82.31% | 37.4318 | 0.72409
|  | Light home retrofit | 5 | N/A | N/A | 19.04% | 82.31% | 17.5742 | 0.31481
|  | Individual measures: | Direct input as alternative to providing numbers above
|  | Space Heating | 20 | x | x | 20% | 56.06% | 12.5698 | 0.25908
|  | Insulation | 15 | x |  | 30% | 56.06% | 18.8547 | 0.38861
|  | Space Cooling | 20 | x | x | 15% | 2.982% | 0.50148 | 0.010336
|  | Insulation | 15 | x |  | 30% | 2.982% | 1.003 | 0.020672
|  | Lighting | 20 | x | x | 50% | 4.223% | 2.3675 | 0.001381
|  | Water Heating | 20 | x | x | 10% | 19.05% | 2.1355 | 0.044014
|  | Fuel Switching (NG) | 0 |  |  | 43.4% | 56.06% | 27.2764 | 2.1289 | Space heating only; Natural Gas to Elec Heat Pump
|  | Fuel Switching (Oil) | 0 |  |  | 48.16% | 56.06% | 30.268 | 3.1117 | Space heating only; Oil to Elec Heat Pump
Renewable Energy
|  | Solar PV (5 kW system) | 0 | N/A | N/A | 20.42% | 100%
|  | Solar Thermal | 0 | N/A | N/A | 40% | 19.05%
Program Benefits Breakdown
|  |  | Program Benefits |  | Baseline |  | Comparison
|  | Measure Category | Total anticipated energy consumption reduction | Total anticipated GHG emission reduction | Baseline energy consumption | Baseline average household GHG emission | % energy consumption reduction | % GHG emission reduction
|  | Unit | GJ/yr | tCO2e/yr | GJ/yr | tCO2e/yr | % | %
Energy Efficiency
|  | Deep home retrofit | 561.4767 | 10.8614 | 1681.671 | 34.661 | 33.39% | 31.34%
|  | Light home retrofit | 87.8708 | 1.574 | 560.557 | 11.5537 | 15.68% | 13.62%
Renewable Energy
|  | Solar PV (5 kW system) | 0 | 0 | 0 | 0 | 0% | 0%
|  | Solar Thermal | 0 | 0 | 0 | 0 | 0% | 0%
Other
|  | Other | 0 | 0 | 0 | 0 | 0% | 0%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hide & password protect - for FCM internal only

## Data (hidden)
CEF Application - Environmental Benefit - Calculation Workbook
Provincial Energy Use & GHG Data
GJ of energy used per household by energy source in residential single family buildings in 2016 across Canada
|  |  | Energy source | BC | AB | SK | MB | ON | QC | NB | NS | NL | PE | TR
|  |  | Electricity | 40.7571 | 18.8188 | 29.0165 | 62.0844 | 35.3893 | 73.7353 | 64.0086 | 41.1324 | 66.6098 | 13.8149 | 33.4542
|  |  | Natural Gas | 45.3177 | 93.1411 | 78.123 | 42.8578 | 68.7869 | 8.312 | 1.9403 | 0.62176 | 0 | 0 | 5.2008
|  |  | Heating Oil | 0.20525 | 0.0035309 | 0.77249 | 0.22503 | 2.871 | 8.182 | 23.8647 | 36.6429 | 18.3417 | 50.5841 | 19.9903
|  |  | Other | 0.46434 | 1 | 1.2207 | 0.32007 | 2.473 | 0.55048 | 0.97131 | 1.4887 | 1.6351 | 0.96475 | 4.8892
|  |  | Wood | 8.9089 | 3.8283 | 3.6085 | 6.6242 | 9.6158 | 33.7646 | 22.1928 | 30.553 | 27.0006 | 32.6901 | 2.7162
|  |  | Total | 95.6532 | 116.7917 | 112.7412 | 112.1114 | 119.136 | 124.5444 | 112.9777 | 110.4388 | 113.5872 | 98.0539 | 66.2506
tCO2e of carbon produced per household by energy source from residential single family buildings in 2016 across Canada
|  |  | Energy source | BC | AB | SK | MB | ON | QC | NB | NS | NL | PE | TR
|  |  | Wood | 0.2092 | 0.089897 | 0.084735 | 0.15555 | 0.2258 | 0.79287 | 0.52113 | 0.71745 | 0.63404 | 0.76764 | 0.06378
|  |  | Electricity | 0.10982 | 4.182 | 5.7227 | 0.036216 | 0.19661 | 0.030723 | 5.8675 | 8.2265 | 0.74011 | 0.78285 | 2.2256
|  |  | Natural Gas | 2.2495 | 4.6281 | 3.6837 | 2.0834 | 3.3474 | 0.40428 | 0.095069 | 0.030464 | 0 | 0 | 0.25483
|  |  | Heating Oil | 0.014554 | 0.00025071 | 0.054777 | 0.015957 | 0.20359 | 0.58019 | 1.6923 | 2.5984 | 1.3006 | 3.587 | 1.4175
|  |  | Other | 0.028397 | 0.061158 | 0.09387 | 0.019576 | 0.15124 | 0.033666 | 0.0594 | 0.091041 | 0.099993 | 0.059004 | 0.29901
Residential energy use by end use (PJ)
|  |  | End-use | BC | AB | SK | MB | ON | QC | NB | NS | NL | PE | Tr
|  |  | Space Heating | 77.1105 | 110.1377 | 27.897 | 28.9406 | 330.4049 | 235.0753 | 23.7327 | 27.8477 | 18.7385 | 3.9821 | 1.2306
|  |  | Water Heating | 39.7213 | 42.8249 | 11.0991 | 9.8333 | 110.8884 | 53.761 | 4.6417 | 6.7885 | 3.134 | 1.1521 | 0.43689
|  |  | Appliances | 27.6756 | 17.15 | 6.9568 | 9.1312 | 64.0155 | 57.2783 | 5.3042 | 6.0588 | 3.6439 | 0.45593 | 0.65638
|  |  | Lighting | 8.3074 | 5.1625 | 2.0386 | 2.1803 | 17.9436 | 14.2848 | 1.1645 | 1.4674 | 0.74974 | 0.10035 | 0.16106
|  |  | Space Cooling | 0.79705 | 0.11056 | 0.55275 | 1.5395 | 28.4105 | 5.1923 | 0.14616 | 0.18874 | 0.004883 | 0.008057 | 0.000101
|  |  | Total | 153.6118 | 175.3856 | 48.5442 | 51.625 | 551.663 | 365.5917 | 34.9893 | 42.3511 | 26.2711 | 5.6985 | 2.485
|  | % share | End-use | BC | AB | SK | MB | ON | QC | NB | NS | NL | PE | Tr
|  |  | Space Heating | 50.2% | 62.8% | 57.47% | 56.06% | 59.89% | 64.3% | 67.83% | 65.75% | 71.33% | 69.88% | 49.52%
|  |  | Water Heating | 25.86% | 24.42% | 22.86% | 19.05% | 20.1% | 14.71% | 13.27% | 16.03% | 11.93% | 20.22% | 17.58%
|  |  | Appliances | 18.02% | 9.778% | 14.33% | 17.69% | 11.6% | 15.67% | 15.16% | 14.31% | 13.87% | 8.001% | 26.41%
|  |  | Lighting | 5.408% | 2.944% | 4.199% | 4.223% | 3.253% | 3.907% | 3.328% | 3.465% | 2.854% | 1.761% | 6.481%
|  |  | Space Cooling | 0.5189% | 0.06304% | 1.139% | 2.982% | 5.15% | 1.42% | 0.4177% | 0.4457% | 0.01859% | 0.1414% | 0.004064%
Heating system stock in residential single family building in 2016 across Canada (thousands of units)
|  |  | Heating system type | BC | AB | SK | MB | ON | QC | NB | NS | NL | PE | Tr
|  |  | Heating Oil | 41.96 | 8.384 | 12.316 | 6.17 | 226.255 | 158.886 | 35.089 | 160.156 | 41.809 | 31.645 | 19.764
|  |  | Gas | 637.024 | 1123.119 | 300.752 | 191.51 | 2532.965 | 61.773 | 10.434 | 5.84 | 3.865 | 0.866 | 5.816
|  |  | Electric & Heat Pump | 408.878 | 83.8 | 34.641 | 157.808 | 765.106 | 1191.33 | 141.922 | 85.385 | 127.028 | 3.587 | 0.79
|  |  | Wood & Other | 27.746 | 14.803 | 12.015 | 7.742 | 58.736 | 18.613 | 29.296 | 8.264 | 10.219 | 2.045 | 4.343
|  |  | Dual Systems | 138.098 | 10.386 | 9.627 | 21.675 | 269.409 | 611.061 | 46.993 | 60.741 | 27.864 | 10.771 | 0
|  |  | TOTAL | 1253.706 | 1240.492 | 369.351 | 384.905 | 3852.471 | 2041.663 | 263.734 | 320.386 | 210.785 | 48.914 | 30.713
|  | Fuel switching | Numerator | BC | AB | SK | MB | ON | QC | NB | NS | NL | PE | Tr
|  |  | Natural Gas Proportion | 6.18% | 0.741% | 3.934% | 3.121% | 8.2% | 72.01% | 77.08% | 96.48% | 91.54% | 97.34% | 77.26%
|  |  | Oil Proportion | 93.82% | 99.26% | 96.07% | 96.88% | 91.8% | 27.99% | 22.92% | 3.518% | 8.462% | 2.664% | 22.74%
Measure data
Solar Production
|  |  | Province | BC: kWh a year /kW installed; SK: 1GJ =; MB: 277.778; ON: kWh
|  |  | AB | BC: 1276
|  |  | SK | BC: 1330
|  |  | NU | BC: 1092
|  |  | NS | BC: 1090
|  |  | NB | BC: 1142
|  |  | NT | BC: 1064
|  |  | YT | BC: 965
|  |  | ON | BC: 1166
|  |  | NL | BC: 949
|  |  | PE | BC: 1104
|  |  | BC | BC: 1004
|  |  | MB | BC: 1272
|  |  | QC | BC: 1183
Other measures
|  |  | Measure Category | BC: Average energy consumption reduction in the category (%)
Energy Efficiency | bar: BC
|  |  | Insulation | BC: 30%
|  |  | Space Heating | BC: 20%
|  |  | Space Cooling | BC: 15%
|  |  | Lighting | BC: 50%
|  |  | Water Heating | BC: 10%
Renewable Energy | bar: BC
|  |  | Solar Thermal | BC: 40%
Fuel Switching
|  |  | Measure Category | BC: Pre-fuel switch furnace efficiency (%); AB: Post-fuel switch heat pump efficiency (%)
|  |  | NG to Elec Heat Pump | BC: 95%; AB: 250%
|  |  | Oil to Elec Heat Pump | BC: 78%; AB: 250%
|  |  | Homes fuel switching (assumption): | AB: 50%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hide & password protect - for FCM internal only
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: http://oee.nrcan.gc.ca/corporate/statistics/neud/dpa/menus/trends/comprehensive_tables/list.cfm & http://data.ec.gc.ca/data/substances/monitor/canada-s-official-greenhouse-gas-inventory/E-Tables-Electricity-Canada-Provinces-Territories/?lang=en
Note on D43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes wood/electric, wood/heating oil, natural gas/electric, heating oil/electric dual systems
Note on B50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: http://oee.nrcan.gc.ca/corporate/statistics/neud/dpa/menus/trends/comprehensive_tables/list.cfm & http://data.ec.gc.ca/data/substances/monitor/canada-s-official-greenhouse-gas-inventory/E-Tables-Electricity-Canada-Provinces-Territories/?lang=en
Note on D71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: FCM Energy Roadmap. Technology Factsheet: Enveloppe. 2019.
Note on D72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: US Department of Energy. Furnaces & Boilers. Retrieved 23.03.2020 from: https://www.energy.gov/energysaver/home-heating-systems/furnaces-and-boilers
Note on D73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: US Department of Energy. Home Cooling Energy Saver 101. Retrieved 23.03.2020 from: https://www.energy.gov/articles/energy-saver-101-infographic-home-cooling
Note on D74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: FCM Energy Roadmap. Technology Factsheet: Lighting & Plug Loads. 2019.
Note on D75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: FCM Energy Roadmap. Technology Factsheet: Water Heating. 2019.
Note on D77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: FCM Energy Roadmap. Technology Factsheet: Water Heating. 2019.
Note on D82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: NRCan. Energy Efficiency Regulations: Gas furnaces. Retrieved 23.03.2020 from: https://www.nrcan.gc.ca/energy-efficiency/energy-efficiency-regulations/guide-canadas-energy-efficiency/gas-furnaces/6879
Note on D83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NRCan. Energy Efficiency Regulations: Oil-fired furnaces. Retrieved 23.03.2020 from: https://www.nrcan.gc.ca/energy-efficiency/energy-efficiency-regulations/guide-canadas-energy-efficiency-regulations/oil-fired-furnaces/6887